## Resources
ResourceID | ResourceName | Team | Role | Active
R001 | Ali Khan | QA-Web | Senior Tester | Yes
R002 | Sara Ahmed | QA-Web | Tester | Yes
R003 | Usman Malik | QA-API | Test Lead | Yes
R004 | Fatima Noor | QA-Mobile | Tester | Yes
R005 | Hassan Raza | QA-API | Automation Eng | Yes

## Projects
ProjectID | ProjectName | ProjectManager | StartDate | TargetEndDate | OverallStatus | Active
P001 | Travel Studio QA | R003 | 2026-01-06 | 2026-06-30 | On Track | Yes
P002 | Mobile App QA | R001 | 2026-02-03 | 2026-08-31 | At Risk | Yes

## CRs
CR_ID | ProjectID | CR_Title | Priority | Status | Owner
CR-1001 | P001 | Login Module Redesign | High | In Progress | R001
CR-1002 | P001 | Booking Search Regression | Medium | In Progress | R003
CR-1003 | P002 | Mobile Auth Flow | High | Open | R004
CR-1004 | P001 | API Rate Limit Testing | Low | Open | R005
CR-1005 | P002 | Push Notification Tests | Medium | In Progress | R002

## Weekly_Log
Year | WeekNumber | WeekStart | WeekEnd | ResourceID | CR_ID | TestCasesPlanned | TestCasesExecuted | TestCasesPassed | TestCasesFailed | BugsReported | BugsClosed | HoursSpent | Notes
2026 | 23 | 2026-06-02 | 2026-06-08 | R001 | CR-1001 | 30 | 28 | 24 | 4 | 5 | 4 | 36
2026 | 23 | 2026-06-02 | 2026-06-08 | R002 | CR-1005 | 20 | 18 | 15 | 3 | 3 | 2 | 32
2026 | 23 | 2026-06-02 | 2026-06-08 | R003 | CR-1002 | 40 | 35 | 30 | 5 | 8 | 6 | 40 | Blocked on env Monday
2026 | 23 | 2026-06-02 | 2026-06-08 | R004 | CR-1003 | 25 | 22 | 20 | 2 | 4 | 3 | 34
2026 | 23 | 2026-06-02 | 2026-06-08 | R005 | CR-1004 | 15 | 14 | 13 | 1 | 2 | 2 | 28
2026 | 24 | 2026-06-09 | 2026-06-15 | R001 | CR-1001 | 30 | 30 | 27 | 3 | 4 | 4 | 38
2026 | 24 | 2026-06-09 | 2026-06-15 | R002 | CR-1005 | 20 | 20 | 18 | 2 | 2 | 2 | 32
2026 | 24 | 2026-06-09 | 2026-06-15 | R003 | CR-1002 | 40 | 38 | 34 | 4 | 6 | 5 | 40
2026 | 24 | 2026-06-09 | 2026-06-15 | R004 | CR-1003 | 25 | 24 | 22 | 2 | 3 | 3 | 36
2026 | 24 | 2026-06-09 | 2026-06-15 | R005 | CR-1004 | 15 | 15 | 14 | 1 | 1 | 1 | 30
2026 | 25 | 2026-06-16 | 2026-06-22 | R001 | CR-1001 | 30 | 29 | 26 | 3 | 3 | 3 | 36
2026 | 25 | 2026-06-16 | 2026-06-22 | R002 | CR-1005 | 20 | 19 | 18 | 1 | 2 | 2 | 30
2026 | 25 | 2026-06-16 | 2026-06-22 | R003 | CR-1002 | 35 | 34 | 31 | 3 | 5 | 4 | 40
2026 | 25 | 2026-06-16 | 2026-06-22 | R004 | CR-1003 | 25 | 23 | 21 | 2 | 4 | 3 | 34 | Device farm issue
2026 | 25 | 2026-06-16 | 2026-06-22 | R005 | CR-1004 | 15 | 15 | 15 | 0 | 1 | 1 | 28
2026 | 26 | 2026-06-23 | 2026-06-29 | R001 | CR-1001 | 30 | 28 | 25 | 3 | 3 | 2 | 36
2026 | 26 | 2026-06-23 | 2026-06-29 | R002 | CR-1005 | 20 | 20 | 19 | 1 | 2 | 2 | 32
2026 | 26 | 2026-06-23 | 2026-06-29 | R003 | CR-1002 | 35 | 35 | 33 | 2 | 4 | 4 | 40
2026 | 26 | 2026-06-23 | 2026-06-29 | R004 | CR-1003 | 25 | 25 | 23 | 2 | 3 | 3 | 36
2026 | 26 | 2026-06-23 | 2026-06-29 | R005 | CR-1004 | 15 | 15 | 15 | 0 | 1 | 1 | 28

## Project_Status_Weekly
Year | WeekNumber | ProjectID | Status | PercentComplete | TestsExecuted | BugsOpen | BugsReported | BugsClosed | ResourcesAssigned | KeyAccomplishments | Risks | Blockers | NextWeekPlan | ReportedBy
2026 | 23 | P001 | On Track | 60 | 97 | 9 | 16 | 12 | 3 | Completed login module test suite | Env instability on Mondays | Waiting on API fix from dev | Start booking regression week 24 | R003
2026 | 23 | P002 | At Risk | 40 | 40 | 7 | 7 | 5 | 2 | Completed auth flow test plan | Device farm availability | iOS simulator version mismatch | Escalate iOS device farm issue | R001
2026 | 24 | P001 | On Track | 65 | 108 | 10 | 13 | 11 | 3 | Login regression 100% executed | Minor API latency spikes | None | Start checkout module testing | R003
2026 | 24 | P002 | At Risk | 48 | 44 | 7 | 5 | 5 | 2 | Fixed iOS simulator issue | Risk: regression scope growing | Still need Android devices | Request additional Android devices | R001
2026 | 25 | P001 | On Track | 72 | 118 | 11 | 11 | 10 | 3 | Booking regression 80% done | None | None | Complete booking regression | R003
2026 | 25 | P002 | Delayed | 50 | 46 | 8 | 6 | 3 | 2 | Push notification tests started | Timeline slipping by 1 week | Missing test data for notifications | Get test data from dev team | R001
2026 | 26 | P001 | On Track | 78 | 123 | 10 | 10 | 10 | 3 | Booking regression complete | None | None | Begin API rate limit testing | R003
2026 | 26 | P002 | At Risk | 55 | 50 | 8 | 5 | 3 | 2 | Push notification basic tests done | Test data still incomplete | Dev team delayed test data delivery | Follow up on test data ETA | R001

## Weekly_Summary
Year | WeekNumber | TotalTestsExecuted | TotalBugsReported | TotalBugsClosed | ActiveResources | ProjectsAtRisk
2026 | 23 | 137 | 23 | 17 | 5 | 1
2026 | 24 | 127 | 17 | 16 | 5 | 1
2026 | 25 | 136 | 17 | 13 | 5 | 1
2026 | 26 | 138 | 15 | 13 | 5 | 1